## Distribution of Work
Task | David | Linda | Tiffany | Ting
Documenting
Writing proposal | L
Writing monthly report for October |  | L
Writing monthly report for November |  |  | L
Writing monthly report for December/January |  |  |  | L
Writing progress report |  | L
Writing final report |  | L
Designing project poster | L
Preparing oral presentation |  |  | L
General Developing
Deciding the development flow | L
Analysing the user requirement (requirement) |  |  |  | L
Drawing the use case model (analysis and design) | L
Investigating OAuth 2.0 (analysis and design) | L
Integrating and testing front end and back end (implementation and testing) |  |  |  | L
Applying for a domain name |  | L
Application UI
Deciding the language of front end |  |  |  | L
Building a mock-up (analysis and design) |  |  |  | L
Building and testing a prototype (implementation and testing) |  |  |  | L
Visualising blockchain for debugging and demonstration (testing) |  |  | L
Blockchain Database
Deciding which database technology (e.g. MongoDB, MySQL, Microsoft SQL Server) to use |  | L
Deciding the language of back end |  |  | L
Investigating blockchain operations (e.g. block generation) |  | L
Investigating blockchain encryption |  |  | L
Investigating P2P technology | L
Building and testing a prototype (implementation and testing) | L
L stands for leader. Every task has a leader, the rest of the teammates assist the leader.

## Gantt Chart
Task | June | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr
Documenting
Writing proposal
Writing monthly report for October
Writing monthly report for November
Writing monthly report for December/January
Writing progress report
Writing final report
Designing project poster
Preparing oral presentation
General Developing
Deciding the development flow
Analysing the user requirement (requirement)
Drawing the use case model (analysis and design)
Investigating OAuth 2.0 (analysis and design)
Integrating and testing front end and back end (implementation and testing)
Applying for a domain name
Application UI
Deciding the language of front end
Building a mock-up (analysis and design)
Building and testing a prototype (implementation and testing)
Visualising blockchain for debugging and demonstration (testing)
Blockchain Database
Deciding which database technology (e.g. MongoDB, MySQL, Microsoft SQL Server) to use
Deciding the language of back end
Investigating blockchain operations (e.g. block generation)
Investigating blockchain encryption
Investigating P2P technology
Building and testing a prototype (implementation and testing)